## Sheet1
Risk Assessment |  |  | v 1.0 - 12 November 2022 |  | GROUP/DISTRICT EXEC RISK REGISTER
Risk category | Risk No | Date added | Risk | Risk owner | Current Controls | Likelihood Score | Impact Score | Overall risk | Value if applicable | Required Actions | Action Owner | Action Completion Date | Trustee review date
Operational | 1 | 2020-02-01 | Loss of use of building - temporary or permanent loss of use of building due to fire, flood or vandalism. | Chair | Building has intruder, fire and smoke alarms which trigger remote notification. Fire extinguishers are in place. Extinguishers and alarms regularly checked/serviced. All access points have high specification locks. Windows protected by grills. Building has insurance cover in place. Informal arrangement for neighbour to monitor the building. Checks with EA have confirmed location is at low risk of flooding. Building is surrounded by a fence with one, lockable, access gate. Building is in use during weekday evenings plus Wednesday mornings and Saturday afternoons. Volunteers have a checklist to follow when closing the building at the end of meetings. PIR floodlights surround the building. | 3 | 4 | 12 |  | Identify local premises that could be used as a temporary meeting place if required. Establish cost of installing CCTV. | IA | 2023-03-31 | April 23 Exec
Financial | 2 | 2020-02-10 | Insufficient funds to operate the building - Group/District income does not cover running costs of the building. Rental income falls below level required. | Treasurer | Significant reserves held. A designated building maintenance fund is operated and subscriptions include an element to top it up. Organisations renting the premises are well supported and content. There is regular liaison with these organisations. Solar panels installed in 2019 have reduced utility bills. | 1 | 4 | 4
Key to scoring of likelihood and impact: 1 = very low, 2 = low, 3 = medium, 4 = high, 5 = very high Overall Risk = likelihood score x impact score
Colour coding: Green 1-6, Amber 8- 15, Red 16-25